Procurement Guidelines

February 2007

“This document has been translated from English in order to reach a wider audience.

While the Asian Development Bank (ADB) has made efforts to verify the accuracy of the

translation, English is the working language of ADB and the English original of this

document is the only authentic (that is, official and authoritative) text. Any citations

must refer to the English original of this document.”

CONTENTS

I. INTRODUCTION 1

1.1 Purpose 1

1.2 General Considerations 2

1.5 Applicability of Guidelines 3

1.6 Eligibility 4

1.9 Advance Contracting and Retroactive

Financing 6

1.10 Joint Ventures 6

1.11 ADB Review 6

1.12 Misprocurement 7

1.13 References to ADB 7

1.14 Fraud and Corruption 8

1.16 Procurement Plan 11

II. INTERNATIONAL COMPETITIVE BIDDING 13

A. General 13

2.1 Introduction 13

2.2 Type and Size of Contracts 13

2.6 Two-Stage Bidding 14

2.7 Notification and Advertising 16

2.9 Prequalification of Bidders 16

B. Bidding Documents 18

2.11 General 18

2.13 Validity of Bids and Bid Security 19

2.15 Language 20

2.16 Clarity of Bidding Documents 20

2.19 Standards 21

2.20 Use of Brand Names 21

2.21 Pricing 22

2.24 Price Adjustment 23

2.26 Transportation and Insurance 23

2.28 Currency Provisions 24

2.29 Currency of Bid 25

2.31 Currency Conversion for Bid Comparison 25

2.32 Currency of Payment 26

2.34 Terms and Methods of Payment 26

2.37 Alternative Bids 27

2.38 Conditions of Contract 27

2.39 Performance Security 28

2.41 Liquidated Damages and Bonus Clauses 29

2.42 Force Majeure 29

2.43 Applicable Law and Settlement of Disputes 29

C. Bid Opening, Evaluation, and Award of Contract 30

2.44 Time for Preparation of Bids 30

2.45 Bid Opening Procedures 30

2.46 Clarifications or Alterations of Bids 31

2.47 Confidentiality 31

2.48 Examination of Bids 31

2.49 Evaluation and Comparison of Bids 32

2.55 Domestic Preferences 34

2.57 Extension of Validity of Bids 34

2.58 Postqualification of Bidders 35

2.59 Award of Contract 35

2.60 Publication of the Award of Contract 35

2.61 Rejection of All Bids 36

2.65 Debriefing 37

D. Modified ICB 37

2.66 Operations Involving a Program of Imports 37

2.68 Procurement of Commodities 38

2.69 Repeat Order 39

III. OTHER METHODS OF PROCUREMENT 41

3.1 General 41

3.2 Limited International Bidding 41

3.3 National Competitive Bidding 42

3.5 Shopping 43

3.6 Direct Contracting 43

3.8 Force Account 45

3.9 Procurement from Specialized Agencies 45

3.10 Procurement Agents 46

3.11 Inspection Agents 46

3.12 Procurement in Loans to Financial

Intermediaries 46

3.13 Procurement under BOO/BOT/BOOT, Concessions

and Similar Private Sector Arrangements 47

3.14 Performance-Based Procurement 48

3.16 Procurement under Loans Guaranteed by ADB 49

3.17 Community Participation in Procurement 49

3.18 Procurement under Disaster and Emergency

Assistance 50

Appendix 1: ADB Review of Procurement Decisions 51

1. Scheduling of Procurement 51

2. Prior Review 51

5. Post Review 54

Appendix 2: Domestic Preferences 56

1. Preference for Domestically Manufactured

Goods 56

7. Preference for Domestic Contractors 58

Appendix 3: Guidance to Bidders 60

1. Purpose 60

2. Responsibility for Procurement 60

3. ADB’s Role 60

5. Information on Bidding 61

6. Bidder’s Role 62

10. Confidentiality 63

11. Action by ADB 63

15. Debriefing 64

I. INTRODUCTION

Purpose

1.1 The purpose of these Guidelines is to inform those carrying out a project that is financed in whole or in part by a loan from the Asian Development Bank (ADB), ADB-financed grant, or ADB-administered funds,1 of the policies that govern the procurement of goods, works, and services (other than consultant services) required for the project. The financing agreement governs the legal relationships between the borrower3 and ADB, and the Guidelines are made applicable to procurement of goods and works for the project, as provided in the agreement. The rights and obligations of the borrower and the providers of goods and works for the project are governed by the bidding documents, and by the contracts signed by the borrower with the providers of goods and

works, and not by these Guidelines or the financing agreements.

No party other than the parties to the financing agreement shall

1 For the purpose of these Guidelines, financing by ADB includes financing by ADB-administered

funds.

2 For the selection and engagement of consultants, see Guidelines on the Use of Consultants

by Asian Development Bank and its Borrowers. References to “goods and works” in these

procurement Guidelines include related services such as transportation, insurance, installation,

commissioning, training, and initial maintenance. The provisions of these procurement

Guidelines also apply to services, such as drilling, mapping, and similar operations.

3 The term “borrower” as used in these Guidelines includes recipients of ADB-financed grants

and ADB-administered funds, and also refers to the executing agency for the project. In

some cases, the borrower acts only as an intermediary, and the project is carried out by

another agency or entity, in which case references in these Guidelines to the borrower

include such agencies and entities, as well as sub-borrowers under onlending arrangements.

2 Procurement Guidelines

4 See para. 1.6, 1.7, and 1.8.

derive any rights therefrom or have any claim to the proceeds of

the financing.

General Considerations

1.2 The responsibility for the implementation of the project, and

therefore for the award and administration of contracts under the

project, rests with the borrower. ADB, for its part, has the obligation

to ensure that the proceeds of its financing are used with due attention

to considerations of economy and efficiency. While in practice

the specific procurement rules and procedures to be followed in the

implementation of a project depend on the circumstances of the

particular case, five basic principles generally guide ADB requirements:

(a) subject to the qualification stated in paragraph 2.11

with regard to procurement under loans or grants from

Special Funds resources, the proceeds of ADB financing

can be used only for procurement of goods and works

supplied from, and produced in, member countries of

ADB, except in any case in which the Board of Directors

determines otherwise under Article 14(ix) of the Articles

of Agreement of ADB;

(b) the need for economy and efficiency in the implementation

of the project, including the procurement of the

goods and works involved;

(c) ADB’s interest in giving all eligible bidders from

developed and developing countries4 the same

information and equal opportunity to compete in

providing goods and works financed by ADB;

(d) ADB’s interest in encouraging the development of

domestic contracting and manufacturing industries in

the country of the borrower; and

I. INTRODUCTION 3

(e) the importance of transparency in the procurement

process.

1.3 Open competition is the basis for efficient public procurement.

Borrowers shall select the most appropriate method for the

specific procurement. In most cases, international competitive

bidding (ICB), properly administered, and with the allowance for

preferences for domestically manufactured goods and, where

appropriate, for domestic contractors5 for works under prescribed

conditions is the most appropriate method. In most cases, therefore,

ADB requires its borrowers to obtain goods, works and services

through ICB open to eligible suppliers and contractors.6 Section II

of these Guidelines describes the procedures for ICB.

1.4 Where ICB is not the most appropriate method of

procurement, other methods of procurement may be used. Section

III describes these other methods of procurement and the

circumstances under which their application would be more

appropriate. The particular methods that may be followed for

procurement under a given project are provided for in the financing

agreement. The specific contracts to be financed under the project,

and their method of procurement, consistent with the financing

agreement, are specified in the procurement plan as indicated in

paragraph 1.16 of these Guidelines.

Applicability of Guidelines

1.5 The procedures outlined in these Guidelines apply to all

contracts for goods and works financed in whole or in part by

ADB.7 For the procurement of those contracts for goods and works

not financed by ADB, the borrower may adopt other procedures.

5 For purposes of these Guidelines, “contractor” refers only to a firm providing construction

services.

6 See para. 1.6, 1.7, and 1.8.

7 This includes those cases where the borrower employs a procurement agent under para.

3.10.

In such cases ADB shall be satisfied that the procedures to be used

will fulfill the borrower’s obligations to cause the project to be

carried out diligently and efficiently, and that the goods and works

to be procured:

(a) are of satisfactory quality and are compatible with the

balance of the project;

(b) will be delivered or completed in timely fashion; and

(c) are priced so as not to affect adversely the economic

and financial viability of the project.

Eligibility

1.6 To foster competition ADB permits bidders from all eligible

member countries to offer goods, works, and services for ADB-financed

projects.8 Any conditions for participation shall be limited

to those that are essential to ensure the bidder’s capability to fulfill

the contract in question.

1.7 In connection with any contract to be financed in whole or

in part by ADB, ADB does not permit a borrower to deny the

participation of a bidder for reasons unrelated to its capability and

resources to successfully perform the contract; nor does it permit a

borrower to disqualify any bidder for such reasons. Consequently,

borrowers should carry out due diligence on the technical and

financial qualifications of bidders to be assured of their capabilities

in relation to the specific contract.

1.8 As exceptions to the foregoing:

(a) Firms of a country or goods manufactured in a country

may be excluded if, by an act of compliance with a

4 Procurement Guidelines

8 See para. 2.11.

decision of the United Nations Security Council taken

under Chapter VII of the Charter of the United Nations,

the borrower’s country prohibits any import of goods

from, or payments to, a particular country, person, or

entity. Where the borrower’s country prohibits payments

to a particular firm or for particular goods by such an

act of compliance, that firm may be excluded.

(b) A firm which has been engaged by the borrower to

provide consulting services for the preparation or

implementation of a project, and any of its affiliates,

shall be disqualified from subsequently providing

goods, works, or services resulting from or directly

related to the firm’s consulting services for such

preparation or implementation. This provision does not

apply to the various firms (consultants, contractors, or

suppliers) which together are performing the

contractor’s obligations under a turnkey or design and

build contract.9

(c) Government-owned enterprises in the borrower’s

country may participate as a bidder only if they can

establish that they (i) are legally and financially

autonomous, (ii) operate under commercial law, and

(iii) are not dependent agencies of the borrower or subborrower.

10

(d) A firm or individual declared ineligible by ADB in accordance

with subparagraph (d) of paragraph 1.14 of these

Guidelines shall be ineligible to be awarded an ADBfinanced

contract during the period of time determined

by ADB.

I. INTRODUCTION 5

9 See para. 2.5.

10 Other than force account units, as permitted under para. 3.8.

Advance Contracting and Retroactive Financing

1.9 ADB encourages borrowers to proceed with the initial steps of

procurement before signing the related financing agreement. In such

cases, the procurement procedures, including advertising, shall be in

accordance with the Guidelines in order for the eventual contracts to

be eligible for ADB financing, and ADB shall review the process used

by the borrower. A borrower undertakes such advance contracting at

its own risk, and any concurrence by ADB with the procedures,

documentation, or proposal for award does not commit ADB to finance

the project in question. If the contract is signed, reimbursement by

ADB of any payments made by the borrower under the contract prior

to signing the financing agreement is referred to as retroactive

financing and is only permitted within the limits specified in the

financing agreement.

Joint Ventures

1.10 Any firm may bid independently or in joint venture confirming

joint and several liability, either with domestic firms and/or with foreign

firms, but ADB does not accept conditions of bidding which require

mandatory joint ventures or other forms of mandatory association

between firms.

ADB Review

1.11 ADB reviews the borrower’s procurement procedures, documents,

bid evaluations, award recommendations, and contracts to ensure

that the procurement process is carried out in accordance with the

agreed procedures. These review procedures are described in Appendix

1. The procurement plan approved by ADB11 shall specify the extent

to which these review procedures shall apply in respect of the

different categories of goods and works to be financed, in whole or

in part by ADB.

6 Procurement Guidelines

11 See para. 1.16.

Misprocurement

1.12 ADB finances expenditures for goods and works that are

procured in accordance with the provisions of the financing

agreement and these Guidelines. If procurement is not carried out

as agreed, ADB will declare misprocurement, and normally cancel

that portion of the financing allocated to the goods and works

that have been misprocured. In appropriate cases, ADB may permit

rebidding after declaring misprocurement. ADB may, in addition,

exercise other remedies provided for under the financing agreement.

Even if a contract is awarded after obtaining a “no objection” from

ADB, ADB reserves the right to declare misprocurement if it

concludes that the “no objection” was issued on the basis of

incomplete, inaccurate, or misleading information or the terms and

conditions of the contract had been substantially modified without

ADB’s approval.

References to ADB

1.13 When the contract is to be financed wholly or partly by ADB,

reference shall be made to ADB in the bidding documents along

the lines of the following language:

“ . . . (name of borrower) . . . has received a loan from the

(ordinary capital resources or Special Funds resources) of

the Asian Development Bank toward the cost of (name of

project), and it is intended that the proceeds of this loan

will be applied to payments under the contract (contracts)

for which this invitation for bids is issued. The terms and

conditions of the contract (contracts) and payments therefore

by the Asian Development Bank will be subject in all

respects to the terms and conditions of the Loan Agreement,

including the Procurement Guidelines. Except as ADB

may specifically otherwise agree, no party other than (name

of borrower) shall derive any rights from the Loan Agreement

or have any claim to the loan proceeds.”

I. INTRODUCTION 7

Fraud and Corruption

1.14 ADB’s anticorruption policy requires borrowers (including

beneficiaries of ADB financed activity), as well as bidders, suppliers,

and contractors under ADB-financed contracts, observe the

highest standard of ethics during the procurement and execution

of such contracts. In pursuance of this policy,12 in the context of

these Guidelines, ADB:

(a) defines, for the purposes of this provision, the terms

set forth below as follows:

(i) “corrupt practice” means the offering, giving,

receiving, or soliciting, directly or indirectly, anything

of value to influence improperly the actions of

another party;

(ii) “fraudulent practice” means any act or omission,

including a misrepresentation, that knowingly or

recklessly misleads, or attempts to mislead, a party

to obtain a financial or other benefit or to avoid

an obligation;

(iii) “coercive practice” means impairing or harming,

or threatening to impair or harm, directly or

indirectly, any party or the property of the party to

influence improperly the actions of a party;

(iv) “collusive practice” means an arrangement

between two or more parties designed to achieve

an improper purpose, including influencing

improperly the actions of another party;

8 Procurement Guidelines

12 See ADB’s Anticorruption Policy (http://www.adb.org/Documents/Policies/Anticorruption)

and Integrity Principles and Guidelines (http://www.adb.org/Documents/Guidelines/Integrity-

Guidelines-Procedures).

(b) will reject a proposal for award if it determines that the

bidder recommended for award has, directly or through

an agent, engaged in corrupt, fraudulent, collusive, or

coercive practices in competing for the contract in

question;

(c) will cancel the portion of the financing allocated to a

contract if it determines at any time that representatives

of the borrower or of a beneficiary of ADB-financing

engaged in corrupt, fraudulent, collusive, or coercive

practices during the procurement or the execution of

that contract, without the borrower having taken timely

and appropriate action satisfactory to ADB to remedy

the situation;

(d) will sanction a party or its successor, including declaring

ineligible, either indefinitely or for a stated period of

time, to participate in ADB-financed activities if it at

any time determines that the firm has, directly or

through an agent, engaged in corrupt, fraudulent,

collusive, or coercive practices in competing for, or in

executing, an ADB-financed contract;

and

(e) will have the right to require that a provision be included

in bidding documents and in contracts financed by ADB,

requiring bidders, suppliers and contractors to permit

ADB or its representative to inspect their accounts and

records and other documents relating to the bid

submission and contract performance and to have them

audited by auditors appointed by ADB.

1.15 (a) With the specific agreement of ADB, a beneficiary of

ADB-financing may introduce an undertaking of the

bidder to observe, in competing for and executing a

contract, the country’s laws against fraud and

I. INTRODUCTION 9

corruption (including bribery), as listed in the bidding

documents. ADB will accept the introduction of such

undertaking at the request of the borrowing country,

provided the arrangements governing such undertaking

are satisfactory to ADB.

(b) When the contract is to be financed wholly or partly by

ADB, the contract documents shall include an

undertaking by the contractor that no fees, gratuities,

rebates, gifts, commissions, or other payments, except

those shown in the bid, have been given or received in

connection with the procurement process or in contract

execution.

(c) ADB considers a conflict of interest to be a situation in

which a party has interests that could improperly

influence that party’s performance of official duties or

responsibilities, contractual obligations, or compliance

with applicable laws and regulations, and that such

conflict of interest may contribute to or constitute a

prohibited practice under the anticorruption policy. In

pursuance of the anticorruption policy’s requirement

that borrowers (including beneficiaries of ADB-financed

activity), as well as bidders, suppliers, and contractors

under ADB-financed contracts, observe the highest

standard of ethics, ADB will take appropriate actions

to manage such conflicts of interest or may reject a

proposal for award if it determines that a conflict of

interest has flawed the integrity of any procurement

process.

10 Procurement Guidelines

Procurement Plan

1.16 As part of the preparation of the project the borrower shall

prepare and, before loan negotiations, furnish to ADB for its

approval, a procurement plan13 acceptable to ADB setting forth:

(a) the particular contracts for the goods, works, and/or services

required to carry out the project during the initial period of at least

18 months; (b) the proposed methods for procurement of such

contracts that are permitted under the financing agreement, and

(c) the related ADB review procedures.14 The borrower shall update

the procurement plan annually or as needed throughout the duration

of the project. The borrower shall implement the procurement

plan in the manner in which it has been approved by ADB.

I. INTRODUCTION 11

13 If the project includes the selection of consulting services, the procurement plan should

also include the methods for selection of consulting services in accordance with Guidelines

on the Use of Consultants by Asian Development Bank and its Borrowers. ADB will disclose

the initial procurement plan to the public after the related financing has been approved;

additional updates will be disclosed after ADB has approved them.

14 See Appendix 1.

II. INTERNATIONAL COMPETITIVE BIDDING

A. General

Introduction

2.1 The objective of international competitive bidding (ICB), as

described in these Guidelines, is to provide all eligible prospective

bidders15 with timely and adequate notification of a borrower’s

requirements and an equal opportunity to bid for the required

goods and works.

Type and Size of Contracts

2.2 The bidding documents shall clearly state the type of

contract to be entered into and contain the proposed contract

provisions appropriate therefor. The most common types of

contracts provide for payments on the basis of a lump sum or

unit prices, or combinations thereof.

2.3 The size and scope of individual contracts will depend on

the magnitude, nature, and location of the project. For projects

requiring a variety of goods and works, separate contracts generally

are awarded for the supply and/or installation of different items of

equipment and plant16 and for the works.

15 See para. 1.6, 1.7 and 1.8.

16 For purposes of these Guidelines, “plant” refers to installed equipment, as in a production

facility.

14 Procurement Guidelines

2.4 For a project requiring similar but separate items of equipment

or works, bids may be invited under alternative contract

options that would attract the interest of both small and large

firms, which could be allowed, at their option, to bid for individual

contracts (slices) or for a group of similar contracts (package). All

bids and combinations of bids shall be received by the same deadline

and opened and evaluated simultaneously so as to determine

the bid or combination of bids offering the lowest evaluated cost

to the borrower.17

2.5 In certain cases ADB may accept or require a turnkey contract

under which the design and engineering, the supply and installation

of equipment, and the construction of a complete facility or

works are provided under one contract. Alternatively, the borrower

may remain responsible for the design and engineering, and invite

bids for a single responsibility contract for the supply and installation

of all goods and works required for the project component.

Design and build, and management contracting18 contracts are

also acceptable where appropriate.19

Two-Stage Bidding

2.6 (a) In the case of turnkey contracts or contracts for large

complex facilities or works of a special nature or complex

information and communication technology, it may be

undesirable or impractical to prepare complete technical

specifications in advance. In such a case, a two-stage

bidding procedure may be used, under which unpriced

17 See para. 2.49–2.54 for the bid evaluation procedures.

18 In construction, a management contractor usually does not perform the work directly

but contracts out and manages the work of other contractors, taking on the full responsibility

and risk for price, quality, and timely performance. Conversely, a construction

manager is a consultant for, or agent of, the borrower, but does not take on such risks.

(If financed by ADB, the services of the construction manager should be procured under

the Guidelines on the Use of Consultants by Asian Development Bank and its Borrowers.

19 Also see para. 3.14 and 3.15 for performance-based contracting.

technical proposals are invited first. These are prepared

on the basis of a conceptual design or performance

specification, and are subject to technical as well as

commercial clarifications and adjustments. The first

stage technical proposal clarification is to be followed

by issuance of amended bidding documents20 and the

submission of final technical proposals and priced bids

in the second stage.

(b) Two-envelope procedures, wherein bids with separate

envelopes for technical and financial proposals are

submitted simultaneously, may be used for the

procurement of goods, works or turnkey contracts. The

borrower has the option to use the two-envelope

procedure with single-stage or two-stage bidding. In

the single-stage, two-envelope procedure, the technical

proposal is opened first and reviewed to determine

responsiveness to the bidding documents. Only the

financial proposals of bidders with responsive technical

proposals are opened for evaluation and comparison.

The financial proposals of bidders whose technical

proposals are not responsive shall be returned

unopened. In the two-stage, two-envelope procedure,

bidders are allowed to amend their technical proposals

in order to ensure conformance to the same technical

standards. Only the financial proposals, including

supplementary price proposals, of bidders whose

original or revised technical proposals are found

conforming to the agreed technical standards, are

opened for evaluation and comparison. The use of these

procedures must be agreed upon by ADB and the

borrower.

20 In revising the bidding documents in the second stage the borrower should respect the

confidentiality of the bidders’ technical proposals used in the first stage, consistent with

requirements of transparency and intellectual property rights.

II. INTERNATIONAL COMPETITIVE BIDDING 15

16 Procurement Guidelines

Notification and Advertising

2.7 Timely notification of bidding opportunities is essential in

competitive bidding. For projects that include ICB the borrower is

required to prepare and submit to ADB a draft general procurement

notice. ADB will arrange for its publication.21 The notice shall contain

information concerning the borrower (or prospective borrower),

amount and purpose of the loan, scope of procurement under

ICB, and the name, telephone number, email address (or fax

number) and address of the borrower’s agency responsible for

procurement and the address of the website where specific

procurement notices will be posted. If known, the scheduled date

for availability of prequalification or bidding documents should be

indicated. Except in the case of advance contracting22 the related

prequalification or bidding documents, as the case may be, shall

not be released to the public earlier than the date of publication of

the general procurement notice.

2.8 Invitations to prequalify or to bid, as the case may be, shall

be advertised as specific procurement notices in ADB’s website as

well as in (i) a newspaper of national circulation in the borrower’s

country (at least in one English language newspaper, if available),

or (ii) on an internationally known and freely accessible website in

English. A copy of the invitation for bids shall be submitted to ADB

for approval and for publication in ADB’s website in accordance

with the provisions of the financing agreement.

Prequalification of Bidders

2.9 Prequalification may be necessary for large or complex works,

or in any other circumstances in which the high costs of preparing

detailed bids could discourage competition, such as customdesigned

equipment, industrial plant, specialized services, some

21 On ADB website: www.adb.org

22 See para. 1.9.

complex information and technology contracts and contracts to

be let under turnkey, design and build, or management contracting.

This also ensures that invitations to bid are extended only to those

who have adequate capabilities and resources. Prequalification shall

be based entirely upon the capability and resources of prospective

bidders to perform the particular contract satisfactorily, taking into

account their (a) experience and past performance on similar

contracts, (b) capabilities with respect to construction or

manufacturing facilities, and (c) financial position.23

2.10 The invitation to prequalify for bidding on specific contracts

or groups of similar contracts shall be advertised and notified as

described in paragraphs 2.7 and 2.8 above. The scope of the

contract and a clear statement of the requirements for qualification

shall be sent to those who responded to the invitation. Generally,

a minimum period of six weeks shall be allowed for the submission

of prequalification applications. There shall be no limits on the

number of bidders to be prequalified, and all found capable of

performing the work satisfactorily in accordance with the approved

prequalification criteria shall be prequalified and invited to submit

bids. As soon as prequalification is completed, the bidding

documents shall be made available to the prequalified prospective

bidders. For prequalification for groups of contracts to be awarded

over a period of time, a limit for the number or total value of

awards to any one bidder may be made on the basis of the bidder’s

resources. The list of prequalified firms in such instances shall be

updated periodically. Verification of the information provided in

the submission for prequalification shall be confirmed at the time

of award of contract, and award may be denied to a bidder that is

judged to no longer have the capability or resources to successfully

perform the contract.

23 ADB has prepared a standard prequalification document for mandatory use by its borrowers,

for appropriate contract types.

II. INTERNATIONAL COMPETITIVE BIDDING 17

18 Procurement Guidelines

B. Bidding Documents

General

2.11 (a) Bidding documents shall state that payments from the

proceeds of ADB loans or grants will be limited to goods

produced in, and services supplied by, member countries

of ADB, except in the case of loans or grants from Special

Funds resources, where payments will be limited to

goods produced in, and services supplied by, developed

member countries that have contributed to such

resources, and all developing member countries.

(b) It is essential that the bidding documents provide all the

information necessary for bidders to prepare responsive

bids. While the detail and complexity of these

documents vary depending upon the kind of goods to

be procured and the size of the contract, they shall

normally include the following: invitation for bids;

instructions to bidders; bidding forms; conditions of

contract, both general and special; technical specifications;

bill of quantities and drawings; schedule of prices;

and necessary appendixes, proforma bid securities and

performance securities.

2.12 (a) Borrowers shall use the appropriate Standard Bidding

Documents (SBDs) issued by ADB with minimum

changes, acceptable to ADB, as necessary to address

project specific conditions. Any such changes shall be

introduced only through bid or contract data sheets,

or through special conditions of contract, and not by

introducing changes in the standard wording of ADB’s

SBDs. Where no relevant standard bidding documents

have been issued, the borrower shall use other internationally

recognized standard conditions of contract and

contract forms acceptable to ADB.

II. PROCEDURES 17

(b) The borrower may use an electronic system to distribute

bidding documents, provided that ADB is satisfied with

its adequacy. If bidding documents are distributed

electronically, the electronic system shall be secure to

avoid modifications to the bidding documents and shall

not restrict the access of bidders to the bidding

documents. Bidding documents must be provided in

print form to bidders who request them. A master copy

of electronic documents shall be retained in print form,

suitably authenticated by signature, stamp or other

instrument acceptable to ADB.

Validity of Bids and Bid Security

2.13 Bidders shall be required to submit bids valid for a period

specified in the bidding documents which shall be sufficient to

enable the borrower to complete the comparison and evaluation

of bids, review the recommendation of award with ADB (if prior

review is required), and obtain all the necessary approvals so that

the contract can be awarded within that period.

2.14 Borrowers have the option of requiring a bid security. When

used, the bid security shall be in the amount and form specified in

the bidding documents24 and shall remain valid for a period of

four weeks beyond the validity period for the bids, in order to

provide reasonable time for the borrower to act if the security is to

be called. Bid security shall be released to unsuccessful bidders once

the contract has been signed with the winning bidder. In place of

a bid security, the borrower may require bidders to sign a declaration

accepting that if they withdraw or modify their bids during the

period of validity or they are awarded the contract and they fail to

sign the contract or to submit a performance security before the

deadline defined in the bidding documents, the bidder will be sus-

24 The bid security, at the bidder’s option, shall be in the form of a certified check, a letter of

credit or a bank guarantee from a reputable bank.

II. INTERNATIONAL COMPETITIVE BIDDING 19

20 Procurement Guidelines

pended for a period of time from being eligible for bidding in any

contract with the borrower.

Language

2.15 Under the Articles of Agreement of ADB, the working language

of ADB is English and therefore bidding and other relevant

documents, including advertisements, shall be prepared in English.

Where more than one language is used, the English version shall

prevail.

Clarity of Bidding Documents

2.16 Bidding documents shall be so worded as to permit and

encourage international competition and shall set forth clearly and

precisely the work to be carried out, the location of the work, the

goods to be supplied, the place of delivery or installation, the schedule

for delivery or completion, minimum performance requirements,

and the warranty and maintenance requirements, as well as any

other pertinent terms and conditions. In addition, the bidding

documents, where appropriate, shall define the tests, standards,

and methods that will be employed to judge the conformity of

equipment as delivered, or works as performed, with the

specifications. Drawings shall be consistent with the text of the

specifications, and an order of precedence between the two shall

be specified.

2.17 The bidding documents shall specify any factors, in addition

to price, which will be taken into account in evaluating bids, and

how such factors will be quantified or otherwise evaluated. If bids

based on alternative designs, materials, completion schedules,

payment terms, etc., are permitted, conditions for their acceptability

and the method of their evaluation shall be expressly stated.

2.18 All prospective bidders shall be provided the same

information, and shall be assured of equal opportunities to obtain

additional information on a timely basis. Borrowers shall provide

reasonable access to project sites for visits by prospective bidders.

For works or complex supply contracts, particularly for those requiring

refurbishing existing works or equipment, a pre-bid conference may

be arranged whereby potential bidders may meet with the borrower

representatives to seek clarifications (in person or online). Minutes

of the conference shall be provided to all prospective bidders with a

copy to ADB. Any additional information, clarification, correction of

errors, or modifications of bidding documents shall be sent to each

recipient of the original bidding documents in sufficient time before

the deadline for receipt of bids to enable bidders to take appropriate

actions. If necessary, the deadline shall be extended. ADB shall receive

a copy and be consulted for issuing a “no objection” when the

contract is subject to prior review.

Standards

2.19 Standards and technical specifications quoted in bidding

documents shall promote the broadest possible competition, while

assuring the critical performance or other requirements for the

goods and/or works under procurement. As far as possible, the

borrower shall specify internationally accepted standards such as

those issued by the International Standards Organization with which

the equipment or materials or workmanship shall comply. Where

such international standards are unavailable or are inappropriate,

national standards may be specified. In all cases, the bidding

documents shall state that equipment, material, or workmanship

meeting other standards, which must specify substantial

equivalence, will also be accepted.

Use of Brand Names

2.20 Specifications shall be based on relevant characteristics and/

or performance requirements. References to brand names, catalog

numbers, or similar classifications shall be avoided. If it is necessary

to quote a brand name or catalog number of a particular

II. INTERNATIONAL COMPETITIVE BIDDING 21

22 Procurement Guidelines

manufacturer to clarify an otherwise incomplete specification, the

words “or equivalent” shall be added after such reference. The

specification shall permit the acceptance of offers for goods which

have similar characteristics and which provide performance at least

substantially equivalent to those specified.

Pricing

2.21 Bids for goods shall be invited on the basis of CIF, or CIP for

all goods offered from abroad, and EXW25 for locally available or

manufactured or assembled goods, including those previously

imported. Where inland transportation, installation, commissioning

or other similar services are required to be performed by the bidder,

as in the case of “supply and installation” contracts, the bidder

shall be required to provide a separate quotation for these services.

2.22 In the case of turnkey contracts, the bidder shall be required

to quote the price of the installed plant at site, including all costs for

supply of equipment, marine and local transportation and insurance,

installation and commissioning, as well as associated works

and all other services included in the scope of contract such as

design, maintenance and operation. Unless otherwise specified in

the bidding documents, the turnkey price shall include all duties,

taxes, and other levies.

2.23 Bidders for civil works contracts shall be required to quote

unit prices or lump sum prices for the performance of the works,

and such prices shall include all duties, taxes and other levies. Bidders

shall be allowed to obtain all inputs (except for unskilled labor)

25 Refer to INCOTERMS 2000 for further definitions. Published by the International Chamber

of Commerce, 38 Cours Albert 1er, 75008 Paris, France. CIF is cost, insurance and freight,

and FOB is free on board, for maritime transportation. CIP is carriage and insurance paid to

(named place of destination), and FCA is free carrier, in the case of multimodal transportation.

EXW is ex works, ex factory or off-the-shelf. The EXW price shall include all duties,

sales and other taxes already paid or payable for the components and raw materials used

in the manufacture or assembly of the equipment, or the prior import of the equipment,

offered in the bid.

from any eligible source so that they may offer the most competitive

bids.

Price Adjustment

2.24 The bidding documents shall clearly indicate whether price

adjustments are allowed in the event changes occur in major cost

components of the contract such as labor, equipment, and

materials, over which the contractor has no control. Price

adjustment provisions are not necessary for simple supply contracts

involving short delivery periods. However, for contracts with long

delivery or completion periods (generally beyond 18 months),

including major civil works contracts, price adjustment provisions

shall be provided. For certain type of equipment where normal

commercial practice requires bidders to submit firm prices regardless

of the delivery time, price adjustment provisions are not needed.

Contracts which contain a large commodity component whose

price may vary sharply in the short term shall contain a price

adjustment clause that protects the borrower or contractor from

losses in case of any abrupt changes in price.

2.25 The amount of price adjustment shall be based on changes

in the cost of the major components of the contract. If used, the

method of adjustment indicated in the bidding documents shall

provide for adjustments calculated using a price adjustment formula

or formulae. The comparison of bid prices shall be carried out on

the basis of base price only.

Transportation and Insurance

2.26 Bidding documents shall permit suppliers and contractors

to arrange transportation and insurance from any eligible source.

Bidding documents shall state the types and terms of insurance to

be provided by the bidder. The indemnity payable under transportation

insurance shall be at least 110 percent of the contract amount

in the currency of the contract or in a freely convertible currency to

II. INTERNATIONAL COMPETITIVE BIDDING 23

24 Procurement Guidelines

enable prompt replacement of lost or damaged goods. For works,

a contractor’s All Risk form of policy usually shall be specified. For

large projects with several contractors on a site, a “wrap-up” or

total project insurance arrangement may be obtained by the borrower,

in which case the borrower shall seek competition for such

insurance.

2.27 As an exception, if a borrower wishes to reserve transportation

and insurance for the import of goods to national companies

or other designated sources, bidders shall be asked to quote FOB,

FCA, CFR (named place), or CPT (named place of destination)26

prices in addition to the CIF or CIP (place of destination) price

specified in paragraph 2.21. Selection of the lowest evaluated bid

shall be on the basis of the CIF or CIP (place of destination) price,

but the borrower may sign the contract on FOB, FCA, CFR, or CPT

terms and make its own arrangement for transportation and/or

insurance. Under such circumstances, the contract shall be limited

to the FOB, FCA, CFR or CPT cost. If the borrower does not wish to

obtain insurance coverage in the market, evidence shall be provided

to ADB that resources are readily available for prompt payment in

a freely convertible currency of the indemnities required to replace

lost or damaged goods.

Currency Provisions

2.28 Bidding documents shall state the currency or currencies in

which bidders are to state their prices, the procedure for conversion

of prices expressed in different currencies into a single currency for

the purpose of comparing bids, and the currencies in which the

contract price will be paid. The following provisions (paragraphs

2.29–2.33) are intended to (a) ensure that bidders have the

opportunity to minimize any exchange risk with regard to the

currency of bid and of payment, and hence may offer their best

26 INCOTERMS 2000 for free carrier (named place) and for carriage paid to (named place of

destination), respectively.

prices; (b) give bidders in countries with weak currencies the option

to use a stronger currency and thus provide a firmer basis for their

bid price; and (c) ensure fairness and transparency in the evaluation

process.

Currency of Bid

2.29 Bidding documents shall state that the bidder may express

the bid price in any currency. If the bidder wishes to express the

bid price as a sum of amounts in different foreign currencies, they

may do so, provided the price includes no more than three foreign

currencies. Furthermore, the borrower may require bidders to state

the portion of the bid price representing local costs incurred in the

currency27 of the country of the borrower.

2.30 In bidding documents for works, the borrower may require

bidders to state the bid price entirely in the local currency, along with

the requirements for payments in up to three foreign currencies of

their choice for expected inputs from outside the borrower’s country,

expressed as a percentage of the bid price, together with the

exchange rates used in such calculations.

Currency Conversion for Bid Comparison

2.31 The bid price is the sum of all payments in various currencies

required by the bidder. For the purpose of comparing prices, bid

prices shall be converted to a single currency selected by the

borrower (local currency or fully convertible foreign currency) and

stated in the bidding documents. The borrower shall make this

conversion by using the selling (exchange) rates for those currencies

quoted by an official source (such as the central bank) or by a

commercial bank or by an internationally circulated newspaper for

similar transactions on a date selected in advance, such source

and date to be specified in the bidding documents, provided that

27 Referred to hereafter as local currency.

II. INTERNATIONAL COMPETITIVE BIDDING 25

26 Procurement Guidelines

the date shall not be earlier than four weeks prior to the deadline

for the receipt of bids, nor later than the original date for the expiry

of the period of bid validity.

Currency of Payment

2.32 Payment of the contract price shall be made in the currency

or currencies in which the bid price is expressed in the bid of the

successful bidder.

2.33 When the bid price is required to be stated in the local currency

but the bidder has requested payment in foreign currencies

expressed as a percentage of the bid price, the exchange rates to

be used for purposes of payments shall be those specified by the

bidder in the bid, so as to ensure that the value of the foreign

currency portions of the bid is maintained without any loss or gain.

Terms and Methods of Payment

2.34 Payment terms shall be in accordance with the international

commercial practices applicable to the specific goods and works,

and shall be made in accordance with the procedures provided in

ADB’s Loan Disbursement Handbook (as amended from time to time).

(a) Contracts for supply of goods shall provide for full

payment on the delivery and inspection, if so required,

of the contracted goods except for contracts

involving installation and commissioning, in which

case a portion of the payment may be made after

the supplier has complied with all its obligations under

the contract. The use of letters of credit is encouraged

so as to assure prompt payment to the supplier. In

major contracts for equipment and plant, provision

shall be made for suitable advances and, in contracts

of long duration, for progress payments during the

period of manufacture or assembly.

(b) Contracts for works shall provide in appropriate cases

for mobilization advances, advances on contractor’s

equipment and materials, regular progress payments,

and reasonable retention amounts to be released upon

compliance with the contractor’s obligations under

contract.

2.35 Any advance payment for mobilization and similar expenses,

made upon signature of a contract for goods or works, shall be

related to the estimated amount of these expenses and be specified

in the bidding documents. Amounts and timing of other

advances to be made, such as for materials delivered to the site

for incorporation in the works, shall also be specified. The bidding

documents shall specify the arrangements for any security

required for advance payments.

2.36 Bidding documents shall specify the payment method and

terms offered, whether alternative payment methods and terms

will be allowed and, if so, how the terms will affect bid evaluation.

Alternative Bids

2.37 The bidding documents shall clearly indicate when bidders

are allowed to submit alternative bids, how alternative bids should

be submitted, how bid prices should be offered and the basis on

which alternative bids shall be evaluated.

Conditions of Contract

2.38 The contract documents shall clearly define the scope of

work to be performed, the goods to be supplied, the rights and

obligations of the borrower and of the supplier or contractor,

and the functions and authority of the engineer, architect, or

construction manager, if one is employed by the borrower, in the

supervision and administration of the contract. In addition to the

general conditions of contract, any special conditions particular to

II. INTERNATIONAL COMPETITIVE BIDDING 27

28 Procurement Guidelines

the specific goods or works to be procured and the location of the

project shall be included. The conditions of contract shall provide

a balanced allocation of risks and liabilities.

Performance Security

2.39 Bidding documents for works shall require security in an

amount sufficient to protect the borrower in case of breach of

contract by the contractor. This security shall be provided in an

appropriate form and amount, as specified by the borrower in the

bidding document.28 The amount of the security may vary,

depending on the type of security furnished and on the nature

and magnitude of the works. A portion of this security shall extend

sufficiently beyond the date of completion of the works to cover

the defects liability or maintenance period up to final acceptance

by the borrower. In addition, retention money to ensure compliance

by the contractor of its warranty or maintenance obligations may

be required in an amount not to exceed 10 percent of the payments.

Such retention money will be withheld until the expiration of the

warranty or maintenance period. After completion of the works,

but before the expiration of the warranty or maintenance period,

the retention money may, at the option of the borrower, be replaced

with a suitable bank guarantee or other appropriate security.

2.40 In contracts for the supply of goods, the need for performance

security depends on the market conditions and commercial

practice for the particular kind of goods. Suppliers or manufacturers

may be required to provide a guarantee to protect against nonperformance

of the contract. Such security in an appropriate amount

may also cover warranty obligations. In addition a percentage of

the payments may be held as retention money to cover warranty

28 The format of the performance security shall be in the form of a bank guarantee, or cash

deposit, in accordance with the standard bidding documents, and shall be issued by a

reputable bank or financial institution selected by the bidder. If the institution issuing the

security is located outside the country of the borrower, it shall have a correspondent financial

institution located in the country of the borrower to make it enforceable.

obligations, and any installation or commissioning requirements.

The security or retention money shall be reasonable in amount.

Liquidated Damages and Bonus Clauses

2.41 Provisions for liquidated damages or similar provisions in an

appropriate amount shall be included in the conditions of contract

when delays in the delivery of goods, completion of works or

failure of the goods or works to meet performance requirements

would result in extra cost, or loss of revenue or loss of other benefits

to the borrower. Provision may also be made for a bonus to be

paid to suppliers or contractors for completion of works or delivery

of goods ahead of the times specified in the contract when such

earlier completion or delivery would be of benefit to the borrower.

Force Majeure

2.42 The conditions of contract shall stipulate that failure on the

part of the parties to perform their obligations under the contract

will not be considered a default if such failure is the result of an

event of force majeure as defined in the conditions of contract.

Applicable Law and Settlement of Disputes

2.43 The conditions of contract shall include provisions dealing with

the applicable law and the forum for the settlement of disputes.

International commercial arbitration has practical advantages over

other methods for the settlement of disputes. Therefore, ADB

recommends that borrowers use this type of arbitration in contracts

for the procurement of goods and works. ADB shall not be named

arbitrator or be asked to name an arbitrator. In case of works

contracts, supply and installation contracts, and turnkey contracts,

the dispute settlement provision shall also include mechanisms such

as dispute review boards or adjudicators, which are designed to

permit a speedier dispute settlement.

II. INTERNATIONAL COMPETITIVE BIDDING 29

30 Procurement Guidelines

C. Bid Opening, Evaluation, and Award of Contract

Time for Preparation of Bids

2.44 The time allowed for the preparation and submission of bids

shall be determined with due consideration of the particular

circumstances of the project and the magnitude and complexity of

the contract. Generally, not less than six weeks from the date of

the invitation to bid or the date of availability of bidding documents,

whichever is later, shall be allowed for ICB. Where large works or

complex items of equipment are involved, a longer period may be

necessary to enable prospective bidders to conduct investigations

before submitting their bids. In such cases, the borrower is

encouraged to convene pre-bid conferences and arrange site visits.

Bidders shall be permitted to submit bids by mail or by hand.

Borrowers may also use electronic systems permitting bidders to

submit bids by electronic means, provided ADB is satisfied with

the adequacy of the system, including, inter alia, that the system is

secure, maintains the confidentiality and integrity of bids submitted,

and employs acceptable management procedures to establish date

and time of submission, and facilitate modification and withdrawal.

Where electronic procurement is used, bidders shall continue to

have the option to submit their bids in print form. The deadline

and place for receipt of bids shall be specified in the invitation for

bids and the bidding documents.

Bid Opening Procedures

2.45 The time for the bid opening shall be the same as for the

deadline for receipt of bids or promptly29 thereafter, and shall be

announced, together with the place for bid opening, in the

invitation to bid. The borrower shall open all bids at the stipulated

time and place. Bids shall be opened in public; bidders or their

representatives shall be allowed to be present (in person or online,

29 To allow sufficient time to take the bids to the place announced for public bid opening.

when electronic bidding is used). The name of the bidder and total

amount of each bid, and of any alternative bids if they have been

requested or permitted, shall be read aloud (and posted online

when electronic bidding is used) and recorded when opened and

a copy of this record shall be promptly sent to ADB and to all

bidders who submitted bids in time. Bids received after the time

stipulated, as well as those not opened and read out at bid opening,

shall not be considered. When electronic bid submission is used,

an online bid opening procedure acceptable to ADB may be

employed.

Clarifications or Alterations of Bids

2.46 Except as otherwise provided in paragraphs 2.6, 2.63, and

2.64 of these Guidelines, bidders shall not be requested or permitted

to alter their bids after the deadline for receipt of bids. The borrower

shall ask bidders for clarification needed to evaluate their bids

but shall not ask or permit bidders to change the substance or

price of their bids after the bid opening. Requests for clarification

and the bidders’ responses shall be made in writing, in hard copy

or by an electronic system satisfactory to ADB.30

Confidentiality

2.47 After the public opening of bids, information relating to the

examination, clarification, and evaluation of bids and recommendations

concerning awards shall not be disclosed to bidders or

other persons not officially concerned with this process until the

publication of contract award.

Examination of Bids

2.48 The borrower shall ascertain whether the bids (a) meet the

eligibility requirements specified in paragraph 1.6, 1.7 and 1.8 of

30 See para. 2.44.

II. INTERNATIONAL COMPETITIVE BIDDING 31

32 Procurement Guidelines

these Guidelines, (b) have been properly signed, (c) are accompanied

by the required securities or required declaration signed as specified

in paragraph 2.14 of the Guidelines, (d) are substantially responsive

to the bidding documents, and (e) are otherwise generally in order.

If a bid is not substantially responsive, that is, it contains material

deviations from or reservations to the terms, conditions, and

specifications in the bidding documents, it shall not be considered

further. The bidder shall not be permitted to correct or withdraw

material deviations or reservations once bids have been opened.31

Evaluation and Comparison of Bids

2.49 The purpose of bid evaluation is to determine the cost to

the borrower of each bid in a manner that permits a comparison

on the basis of their evaluated cost. Subject to paragraph 2.58,

the bid with the lowest evaluated cost,32 but not necessarily the lowest

submitted price, shall be selected for award.

2.50 The bid price read out at the bid opening shall be adjusted

to correct any arithmetical errors. Also, for the purpose of

evaluation, adjustments shall be made for any quantifiable

nonmaterial deviations or reservations. Price adjustment provisions

applying to the period of implementation of the contract shall not

be taken into account in the evaluation.

2.51 The evaluation and comparison of bids shall be on CIF or

CIP (place of destination) prices for the supply of imported goods33

and EXW prices, plus cost of inland transportation and insurance

to the place of destination, for goods manufactured within the

31 See para. 2.50 regarding corrections, and para. 2.6 regarding clarifications in two-stage

and two-envelope procedures.

32 See para. 2.52.

33 Borrowers may ask for prices on a CIF basis (and bids compared on that same basis) only

when the goods are carried by sea and the goods are not containerized. CIF shall not be

used for anything other than sea transport. In the case of manufactured goods, it is unlikely

that the choice of CIF will be appropriate, because these goods are usually containerized.

CIP can be used for any mode of transport, including sea and multimodal transport.

borrower’s country, together with prices for any required

installation, training, commissioning, and other similar services.34

2.52 Bidding documents shall also specify the relevant factors, in

addition to price, to be considered in bid evaluation, and the manner

in which they will be applied for the purpose of determining the

lowest evaluated bid. For goods and equipment, other factors may

be taken into consideration including, among others, payment

schedule, delivery time, operating costs, efficiency and compatibility

of the equipment, availability of service and spare parts, and related

training, safety, and environmental benefits. The factors other than

price to be used for determining the lowest evaluated bid shall, to

the extent practicable, be expressed in monetary terms in the

evaluation provisions of the bidding documents. Bids shall be

compared on the basis of base price without taking into account

the provisions for price adjustments. Likewise, customs duties and

import taxes on goods to be imported shall be excluded in

comparing bids for the supply of goods.

2.53 Under works contracts, contractors are responsible for all

duties, taxes, and other levies, and bidders shall take these factors

into account in preparing their bids. The evaluation and comparison

of bids shall be on this basis. Turnkey contracts shall be evaluated

excluding taxes and duties for the goods component.35 Bid

evaluation for works shall be strictly in monetary terms. Any procedure

under which bids above or below a predetermined assessment of

bid values are automatically disqualified is not acceptable. If time is

a critical factor, the value of early completion to the borrower may

be taken into account according to criteria presented in the bidding

documents, only if the conditions of contract provide for

commensurate penalties for noncompliance.

34 The evaluation of bids shall not take into account: (a) customs duties and other taxes levied

on imported goods quoted CIF or CIP (which exclude custom duties); and (b) sales and

similar taxes levied in connection with the sale or delivery of the goods.

35 Unless bidding documents specify otherwise for some turnkey contracts (see para. 2.22).

II. INTERNATIONAL COMPETITIVE BIDDING 33

34 Procurement Guidelines

2.54 The borrower shall prepare a detailed report on the evaluation

and comparison of bids setting forth the specific reasons on which

the recommendation is based for the award of the contract.

Domestic Preferences

2.55 At the request of the borrower, and under conditions to be

agreed under the financing agreement and set forth in the bidding

documents, a margin of preference may be provided in the

evaluation of bids for:

(a) goods manufactured in the country of the borrower

when comparing bids offering such goods with those

offering goods manufactured abroad; and

(b) works in member countries below a specified threshold

of GNP36 per capita, when comparing bids from eligible

domestic contractors with those from foreign firms.

2.56 Where preference for domestically manufactured goods or

for domestic contractors is allowed, the methods and stages set

forth in Appendix 2 to these Guidelines shall be followed in the

evaluation and comparison of bids.

Extension of Validity of Bids

2.57 Borrowers shall complete evaluation of bids and award of

contract within the initial period of bid validity so that extensions are

not necessary.37 An extension of bid validity, if justified by exceptional

circumstances, shall be requested in writing from all bidders before

the expiration date. The extension shall be for the minimum period

required to complete the evaluation, obtain the necessary approvals,

and award the contract. Whenever an extension of bid validity period

36 Gross national product as defined annually by ADB.

37 See Appendix 1, para. 2(d).

is requested, bidders shall not be requested or be permitted to change

the price or other conditions of their bid. Bidders shall have the right

to refuse to grant such an extension. If the bidding documents

require a bid security, bidders may exercise their right to refuse to

grant such an extension without forfeiting their bid security, but those

who are willing to extend the validity of their bid shall be required

to provide a suitable extension of bid security.

Postqualification of Bidders

2.58 If bidders have not been prequalified, the borrower shall

determine whether the bidder whose bid has been determined to

offer the lowest evaluated cost has the capability and resources to

effectively carry out the contract as offered in the bid. The criteria

to be met shall be set out in the bidding documents, and if the

bidder does not meet them, the bid shall be rejected. In such an

event, the borrower shall make a similar determination for the next

lowest evaluated bidder.

Award of Contract

2.59 The borrower shall award the contract, within the period of

the validity of bids, to the bidder who meets the appropriate

standards of capability and resources and whose bid has been

determined (i) to be substantially responsive to the bidding

documents and (ii) to offer the lowest evaluated cost.38 A bidder

shall not be required, as a condition of award, to undertake

responsibilities for work not stipulated in the bidding documents

or otherwise to modify the bid as originally submitted.

Publication of the Award of Contract

2.60 Within two weeks of receiving ADB’s “no objection” to the

recommendation of contract award, the borrower shall publish in

38 Referred to as “lowest evaluated bidder” and “lowest evaluated bid,” respectively.

II. INTERNATIONAL COMPETITIVE BIDDING 35

36 Procurement Guidelines

an English language newspaper or well-known and freely accessible

website the results identifying the bid and lot numbers, and the

following information: (a) name of each bidder who submitted a

bid; (b) bid prices as read out at bid opening; (c) name and evaluated

prices of each bid that was evaluated; (d) name of bidders whose

bids were rejected and the reasons for their rejection; and (e) name

of the winning bidder, and the price it offered, as well as the

duration and summary scope of the contract awarded. For contracts

subject to post review, the borrower shall publish the results no

later than the date of contract award.

Rejection of All Bids

2.61 Bidding documents usually provide that borrowers may

reject all bids. Rejection of all bids is justified when there is

lack of effective competition, or bids are not substantially

responsive or when bid prices are substantially higher than

existing budget. Lack of competition shall not be determined

solely on the basis of the number of bidders. Even when only

one bid is submitted, the bidding process may be considered valid,

if the bid was satisfactorily advertised and prices are reasonable in

comparison to market values. Borrowers may, after ADB’s prior

approval, reject all bids. If all bids are rejected, the borrower

shall review the causes justifying the rejection and consider

making revisions to the conditions of contract, design and

specifications, scope of the contract, or a combination of these,

before inviting new bids.

2.62 If the rejection of all bids is due to lack of competition, wider

advertising shall be considered. If the rejection is due to most or all

of the bids being nonresponsive, new bids may be invited from the

initially prequalified firms, or with the agreement of ADB from only

those that submitted bids in the first instance.

2.63 When all bids have been rejected, a rebidding may be called,

and the borrower shall request for new bids from all who were

supplied with bidding documents in the first instance. However, if

there has been a sufficient number of bids in the initial bidding,

the borrower may consider inviting bids only from those who have

previously submitted bids. Where all bid prices substantially exceed

the cost estimates, the borrower may, instead of calling for

new bids, and after consultation with ADB, negotiate with the

lowest evaluated bidder for a reduction of the bid price. If no satisfactory

contract can be concluded and a rebidding is called, modification

of the scope of the contract shall be considered.

2.64 ADB’s prior approval shall be obtained before rejecting all

bids, soliciting new bids, or entering into negotiations with the

lowest evaluated bidder.

Debriefing

2.65 In the publication of contract award referred to in paragraph

2.60 the borrower shall specify that any bidder who wishes

to ascertain the grounds on which its bid was not selected, should

request an explanation from the borrower. The borrower shall

promptly provide an explanation of why such bid was not selected,

either in writing and/or in a debriefing meeting, at the option of

the borrower. The requesting bidder shall bear all the costs of attending

such a debriefing.

D. Modified ICB

Operations Involving a Program of Imports

2.66 Proceeds of a program loan may be utilized to finance

economy-wide import requirements on the basis of a negative

import list, or sector-specific import requirements on the basis of a

positive import list. Normally, negative import lists will be appropriate,

although positive lists may also be applied, for example

when foreign exchange is scarce and ADB wishes to ensure that

sector import requirements are met. Documentation in respect of

II. INTERNATIONAL COMPETITIVE BIDDING 37

38 Procurement Guidelines

specific imports is required for program loans for which a positive

list of eligible items is utilized.

2.67 ADB’s normal ICB procedures are not required for contracts

financed under program loans. For goods commonly traded in

international commodity markets (e.g., petroleum products and

fertilizers), normal commercial procedures appropriate to the trade

are regarded as acceptable for ADB financing. Financing of specific

commodities may be limited to an agreed upon maximum

percentage (say 60% of the total loan amount). The specific

procurement procedures proposed for each program loan are based

on ADB’s assessment of the procedures in the borrowing DMC

and are set out in the loan documentation. The borrower and,

where appropriate, concerned agencies are required to keep

accurate records of the accounts under the program loan.

Procurement of Commodities

2.68 Market prices of commodities, such as grain, animal feed,

cooking oil, fuel, fertilizer, and metals, fluctuate, depending upon

the demand and supply at any particular time. Many are quoted in

established commodity markets. Procurement often involves

multiple awards for partial quantities to assure security of supply

and multiple purchases over a period of time to take advantage of

favorable market conditions and to keep inventories low. A list of

prequalified bidders may be drawn up to whom periodic invitations

are issued. Bidders may be invited to quote prices linked to the

market price at the time of or prior to the shipments. Bid validities

shall be as short as possible. A single currency in which the commodity

is usually priced in the market, may be used for bidding and

payment. The currency shall be specified in the bidding document.

Bidding documents may permit faxed bids or bids submitted by

electronic means, and in such cases either no bid security is required,

or standing bid securities may be submitted by prequalified

bidders valid over a specified period of time. Standard contract

conditions and forms consistent with market practices shall be used.

Repeat Order

2.69 Where, after the items originally envisaged for the project

have been procured through international competitive bidding,

an additional quantity of the same items is urgently needed to

meet the requirements of the project and funds are available for

this purpose, the additional items may be procured through repeat

order bidding where it can be shown clearly that no advantage

could be gained by adopting full international competitive

bidding.39 Under this procedure, bids may be invited only from

those who submitted responsive bids for the original order or, if

there was a large number of responsive bidders, only from the five

lowest responsive bidders.

39 Also see para. 3.6(a).

II. INTERNATIONAL COMPETITIVE BIDDING 39

III. OTHER METHODS OF PROCUREMENT

General

3.1 This Section describes the methods of procurement that can

be used where international competitive bidding (ICB) would not

be the most economic and efficient method of procurement, and

where other methods are deemed more appropriate.40 ADB’s

policies with respect to margins of preference for domestically

manufactured goods and works contracts do not apply to methods

of procurement other than ICB. Paragraphs 3.2 to 3.7 describe the

generally used methods in descending order of preference and the

remaining paragraphs the methods used in specific circumstances.

Limited International Bidding

3.2 Limited international bidding (LIB) is essentially ICB by direct

invitation without open advertisement. It may be an appropriate

method of procurement where (a) there is only a limited number

of suppliers, (b) the amount of the contract is not large enough to

attract foreign suppliers and contractors through ICB, or (c) other

exceptional reasons may justify departure from full ICB procedures.

Under LIB, borrowers shall seek bids from a list of potential suppliers

broad enough to assure competitive prices, such list to include all

40 Contracts shall not be divided into smaller units in order to make them less attractive for

ICB procedures; any proposal to divide a contract into smaller packages shall require the

prior approval of ADB.

suppliers when there are only a limited number. Domestic preferences

are not applicable in the evaluation of bids under LIB. In all

respects other than advertisement and preferences, ICB procedures

shall apply, including the publication of the award of contract as

indicated in paragraph 2.60.

National Competitive Bidding

3.3 National competitive bidding (NCB) is the competitive

bidding procedure normally used for public procurement in the

country of the borrower, and may be the most appropriate way of

procuring goods or works which, by their nature or scope, are

unlikely to attract foreign competition. To be acceptable for use in

ADB-financed procurement, these procedures shall be reviewed and

modified41 as necessary to assure economy, efficiency, transparency,

and broad consistency with the provisions included in Section

I of these Guidelines. NCB may be the most appropriate method of

procurement where foreign bidders are not expected to be interested

because (a) the contract values are small, (b) works are scattered

geographically or spread over time, (c) works are labor intensive,

or (d) the goods or works are available locally at prices below

the international market. NCB procedures may also be used where

the advantages of ICB are clearly outweighed by the administrative

or financial burden involved.

3.4 Advertising may be limited to the national press or official

gazette, or a free and open access website. Bidding documents

may be only in a national language of the borrower’s country (or

the language used nation-wide in the borrower’s country for

commercial transactions), and the currency of the country of the

borrower is generally used for the purposes of bidding and

payment. In addition, the bidding documents shall provide clear

instructions on how bids should be submitted, how prices should

be offered, and the place and time for submission of bids. Adequate

41 Any such modification shall be reflected in the financing agreement.

42 Procurement Guidelines

III. OTHER METHODS OF PROCUREMENT 43

response time for preparation and submission of bids shall be

provided. The procedures shall provide for adequate competition

in order to ensure reasonable prices, and methods used in the

evaluation of bids and the award of contracts shall be objective

and made known to all bidders in the bidding documents and not

be applied arbitrarily. The procedures shall also include public

opening of bids, publication of results of evaluation and of the

award of contract and provisions for bidders to protest. If foreign

firms wish to participate under these circumstances, they shall be

allowed to do so.

Shopping

3.5 Shopping is a procurement method based on comparing

price quotations obtained from several suppliers (in the case of

goods) or from several contractors (in the case of civil works), with

a minimum of three, to assure competitive prices, and is an

appropriate method for procuring readily available off-the-shelf

goods or standard specification commodities of small value, or

simple civil works of small value. Requests for quotations shall

indicate the description and quantity of the goods or specifications

of works, as well as desired delivery (or completion) time and place.

Quotations may be submitted by letter, facsimile or by electronic

means. The evaluation of quotations shall follow the same principles

as of open bidding. The terms of the accepted offer shall be

incorporated in a purchase order or brief contract.

Direct Contracting

3.6 Direct contracting is contracting without competition (single

source) and may be an appropriate method under the following

circumstances:

(a) Additional items are required under an existing contract,

which was awarded in accordance with ICB procedures.

ADB shall be satisfied in such cases that no better offer

44 Procurement Guidelines

is likely to be received, and that the price to be paid is

not more than the original price. Usually, the repeat

order shall occur within 18 months of the original order

while the additional quantities shall not exceed 30 percent

of the original quantities.

(b) Standardization of equipment or spare parts, to be

compatible with existing equipment, may justify additional

purchases from the original supplier. For such

purchases to be justified, the original equipment shall

be suitable, the number of new items shall generally

be less than the existing number, the price shall be

reasonable, and the advantages of another make or

source of equipment shall have been considered and

rejected on grounds acceptable to ADB.

(c) The required equipment is proprietary and obtainable

only from one source.

(d) The contractor responsible for a process design requires

the purchase of critical items from a particular supplier

as a condition of a performance guarantee.

(e) Where civil works are to be contracted that are a natural

extension of an earlier or ongoing job and it can be

shown that the engagement of the same contractor

will be more economical and will ensure compatibility

of results in terms of quality of work.

(f) In exceptional cases, such as in response to natural

disasters.

3.7 After the contract signature, the borrower shall publish in

an English language newspaper or in English on a well-known and

freely accessible website the name of the contractor, price, duration,

and summary scope of the contract. This publication may be

III. OTHER METHODS OF PROCUREMENT 45

done quarterly and in the format of a summarized table covering

the previous period.

Force Account

3.8 Force account, that is, construction by the use of the

borrower’s own personnel and equipment,42 may be the only

practical method for constructing some kinds of works. The use of

force account may be justified where:

(a) quantities of work involved cannot be defined in advance;

(b) works are small and scattered or in remote locations

for which qualified construction firms are unlikely to

bid at reasonable prices;

(c) work is required to be carried out without disrupting

ongoing operations;

(d) risks of unavoidable work interruption are better borne

by the borrower than by a contractor; or

(e) there are emergencies needing prompt attention.

Procurement from Specialized Agencies

3.9 There may be situations in which procurement directly from

specialized agencies, acting as suppliers, pursuant to their own

procedures, may be the most appropriate way of procuring:

(a) small quantities of off-the-shelf goods, primarily in the fields of

education and health; and (b) specialized products where the

number of suppliers is limited such as for vaccines or drugs.

42 A government-owned construction unit that is not managerially and financially autonomous

shall be considered a force account unit. “Force account” is otherwise known as

“direct labor,” “departmental forces,” or “direct work.”

46 Procurement Guidelines

Procurement Agents

3.10 Where borrowers lack the necessary organization, resources,

and experience, borrowers may wish (or be required by ADB) to

employ, as their agent, a firm specializing in handling procurement.

The agent shall follow all the procurement procedures provided

for in the financing agreement and the Guidelines, including use

of ADB SBDs, review procedures, and documentation. This also

applies in cases where UN agencies act as procurement agents.43

Management contractors may be employed in a similar manner

for a fee to contract for miscellaneous works involving reconstruction,

repairs, rehabilitation, and new construction in emergency

situations, or where large numbers of small contracts are involved.

Inspection Agents

3.11 Preshipment inspection and certification of imports is one

of the safeguards for the borrower, particularly where the country

has a large import program. The inspection and certification usually

covers quality, quantity, and reasonableness of price. Imports

procured through competitive bidding procedures shall not be

subject to price verification, but only verification for quality and

quantity. However, imports not procured through ICB may

additionally be subjected to price verification. The inspection agents

are ordinarily paid for on a fee basis levied on the value of the

goods. Costs for certification of imports shall not be considered in

the evaluation of bids under ICB.

Procurement in Loans to Financial Intermediaries

3.12 Where the financing provides funds to an intermediary

institution such as an agricultural credit institution or a development

43 The Guidelines on the Use of Consultants by Asian Development Bank and its Borrowers

shall apply for the selection of procurement and inspection agents. The cost or fee of the

procurement or inspection agent is eligible for financing from ADB, if so provided in the

financing agreement, and provided the terms and conditions of selection and employment

are acceptable to ADB.

III. OTHER METHODS OF PROCUREMENT 47

finance company, to be re-lent to beneficiaries such as individuals,

private sector enterprises, small and medium enterprises, or

autonomous commercial enterprises in the public sector for the

partial financing of subprojects, the procurement is usually

undertaken by the respective beneficiaries in accordance with

established private sector or commercial practices, which are

acceptable to ADB. However, even in these situations, ICB may be

the most appropriate procurement method for the purchase of

large single items or in cases where large quantities of like goods

can be grouped together for bulk purchasing.

Procurement under BOO/BOT/BOOT, Concessions and

Similar Private Sector Arrangements

3.13 In the case of loans made by ADB to the private sector

without government guarantee, ADB does not insist on ICB

procedures, but will request borrowers to satisfy ADB that

procurement procedures have been applied in a transparent

manner, preferably through competitive bidding procedures, and

that the goods and works procured are from eligible member

countries and are suitable for the project. Where ADB is participating

in financing a BOO/BOT/BOOT44 or similar type of project, either

of the following procurement procedures shall be used:

(a) The project sponsor for a BOO/BOT/BOOT or similar type

of project shall be selected in a transparent manner,

preferably through competitive bidding procedures

acceptable to ADB, which may include several stages in

order to arrive at the optimal combination of criteria

for the purpose of establishing the most economic and

efficient proposal, such as the performance

specifications of the facility offered, the cost charged

to the user or purchaser, and the period of the facility

44 BOO= build, own, operate; BOT= build, operate, transfer; BOOT= build, own, operate,

transfer

48 Procurement Guidelines

depreciation. The project sponsor selected in this

manner shall then be free to procure the goods and

works required for the facility from eligible member

countries, using suitable procedures.

Or,

(b) If the project sponsor has not been selected in the

manner set forth in sub-paragraph (a) above, the goods

and works required for the facility and to be financed

by ADB, shall be procured from eligible member

countries in a transparent manner, through competitive

bidding procedures acceptable to ADB.

Performance-Based Procurement

3.14 Performance based procurement,45 also called output-based

procurement, refers to competitive procurement processes (ICB or

NCB) resulting in a contractual relationship where payments are

made for measured outputs instead of the traditional way where

inputs are measured. The technical specifications define the desired

result and which outputs will be measured including how they will

be measured. Those outputs aim at satisfying a functional need

both in terms of quality, quantity and reliability. Payment is made

in accordance with the quantity of outputs delivered, subject to

their delivery at the level of quality required. Reductions from

payments (or retentions) may be made for lower-quality level of

outputs and, in certain cases, premiums may be paid for higher

quality level of outputs. The bidding documents do not normally

prescribe the inputs, nor a work method for the contractor. The

contractor is free to propose the most appropriate solution, based

on mature and well proven experience and shall demonstrate that

45 The use of performance based procurement in ADB-financed projects should be the result

of the satisfactory technical analysis of the different options available and should be either

included in the financing agreement or subject to prior approval by ADB for incorporation

into the procurement plan.

the level of quality specified in the bidding documents will be

achieved.

3.15 Performance based procurement (or output based procurement)

can involve: (a) the provision of services to be paid on the

basis of outputs; (b) design, supply, construction (or rehabilitation)

and commissioning of a facility to be operated by the borrower;

or (c) design, supply, construction (or rehabilitation) of a facility and

provision of services for its operation and maintenance for a defined

period of years after its commissioning.46 For the cases where

design, supply and/or construction are required, prequalification is

normally required and the use of two-stage bidding as indicated

in paragraph 2.6 shall apply.

Procurement under Loans Guaranteed by ADB

3.16 If ADB guarantees the repayment of a loan made by another

lender, the goods and works financed by the said loan shall be

procured with due attention to economy and efficiency and in

accordance with procedures which meet the requirements of

paragraphs 1.2 and 1.5.

Community Participation in Procurement

3.17 Where, in the interest of project sustainability, or to achieve

certain specific social objectives of the project, it is desirable in

selected project components to (a) call for the participation of local

communities and/or nongovernmental organizations (NGOs) in the

delivery of services, or (b) increase the utilization of local knowhow

and materials, or (c) employ labor-intensive and other

III. OTHER METHODS OF PROCUREMENT 49

46 Examples of such type of procurement are: (i) for the case of procurement of services:

provision of medical services, i.e. payments for specific services, like office visits, or defined

laboratory tests, etc. ; (ii) for the case of procurement of a facility: design, procurement,

construction, and commissioning of a thermal power plant to be operated by the borrower;

(iii) for the case of procurement of a facility and services: design, procurement,

construction (or rehabilitation) of a road and operation and maintenance of the road for

5 years after construction.

appropriate technologies, the procurement procedures,

specifications, and contract packaging shall be suitably adapted to

reflect these considerations, provided these are efficient and are

acceptable to ADB. The procedures proposed and the project

components to be carried out by community participation shall be

outlined in the financing agreement and further elaborated in the

procurement plan or the relevant project implementation document

approved by ADB.

Procurement under Disaster and Emergency

Assistance

3.18 Procurement of goods and works under disaster and

emergency assistance shall incorporate greater flexibility. ICB

requirements will be relaxed in favor of NCB with an abbreviated

bidding period. LIB will be the norm for procurement of goods

with minimum bidding periods ranging from one to two weeks.

Direct contracting to contractors and suppliers under existing loans

or grants will be allowed for new contracts, with rates negotiated

around those in effect for the existing contract with adjustments

as required for inflation and physical considerations. Similarly,

contractors and suppliers competitively selected under projects

financed by other donors will be considered for direct contracting

for new ADB-financed contracts.

50 Procurement Guidelines

Appendix 1

ADB REVIEW OF PROCUREMENT DECISIONS

Scheduling of Procurement

1. ADB shall review the procurement arrangements proposed

by the borrower in the procurement plan for its conformity with

the financing agreement and these Guidelines. The procurement

plan shall cover an initial period of at least 18 months. The borrower

shall update the procurement plan on an annual basis or as

needed always covering the next 18 months period of project

implementation. Any revisions proposed to the procurement plan

shall be furnished to ADB for its prior approval.

Prior Review

2. With respect to all contracts47 which are subject to ADB’s

prior review:

(a) In cases where prequalification is used, the borrower

shall, before prequalification submissions are invited,

furnish ADB with the draft documents to be used,

including the text of the invitation to prequalify, the

prequalification documents (including instructions to

applicants, qualification criteria, application forms, and

scope of contract), and the evaluation methodology,

together with a description of the advertising

procedures to be followed, and shall introduce such

modifications in said procedure and documents, as ADB

shall reasonably request. The report evaluating the

applications received by the borrower, the list of

47 For contracts procured on the basis of direct contracting under paras. 3.6 and 3.7, the

borrower shall furnish to ADB for its approval, prior to contract execution, a copy of the

specifications and the draft contract. The contract shall be executed only after ADB has

given its approval, and the provisions in (h) of this paragraph shall apply with respect to

the executed contract.

APPENDIX 1 ADB REVIEW OF PROCUREMENT DECISIONS 51

proposed prequalified bidders, together with a

statement of their qualifications and of the reasons for

the exclusion of any applicant for prequalification, shall

be furnished by the borrower to ADB for its comments

before the applicants are notified of the borrower’s

decision, and the borrower shall make such additions

to, deletions from, or modifications in the said list as

ADB shall reasonably request.

(b) Before bids are invited, the borrower shall furnish to

ADB for its comments, draft bidding documents,

including the invitation to bid; instructions to bidders,

including the basis of bid evaluation and contract

award; and the conditions of contract and specifications

for the civil works, supply of goods, or installation

of equipment, etc., as the case may be, together

with a description of the advertising procedures to be

followed for the bidding (if prequalification has not

been used), and shall make such modifications in the

said documents as ADB shall reasonably request. Any

further modification shall require ADB’s approval before

it is issued to the prospective bidders.

(c) After bids have been received and evaluated, the

borrower shall, before a final decision on the award is

made, furnish to ADB, at least four weeks prior to

expiration of bid validity, a detailed report (prepared, if

ADB shall so request, by experts acceptable to ADB),

on the evaluation and comparison of the bids received,

together with the recommendations for award and such

other information as ADB shall reasonably request. ADB

shall, if it determines that the intended award would

be inconsistent with the financing agreement and/or

the procurement plan, promptly inform the borrower

and state the reasons for such determination.

Otherwise, ADB shall provide its no objection to the

52 Procurement Guidelines

recommendation for contract award. The borrower shall

award the contract only after receiving the “no

objection” from ADB.

(d) If the borrower requires an extension of bid validity to

complete the process of evaluation, obtain necessary

approvals and clearances, and to make the award, it

should seek ADB’s prior approval for the first request

for extension, if it is longer than four weeks, and for all

subsequent requests for extension, irrespective of the

period.

(e) If after publication of the results of evaluation, the borrower

receives protests or complaints from bidders, a

copy of the complaint and a copy of the borrower’s

response shall be sent to ADB for information.

(f) If as result of analysis of a protest the borrower changes

its contract award recommendation, the reasons for

such decision and a revised evaluation report shall be

submitted to ADB for no objection. The borrower shall

provide a republication of the contract award in the

format of paragraph 2.60 of these Guidelines.

(g) The terms and conditions of a contract shall not, without

ADB’s prior approval, materially differ from those

on which bids were asked or prequalification of contractors,

if any, was invited.

(h) Promptly after each contract is awarded, ADB shall be

furnished with three copies of the contract as executed.

If the final contract proposed to be executed differs

substantially from the draft contract previously approved

by ADB, or if any substantial amendment of the contract

is proposed after its execution, the proposed

changes shall be submitted to ADB for prior approval.

APPENDIX 1 ADB REVIEW OF PROCUREMENT DECISIONS 53

(i) All evaluation reports shall be accompanied by a

summary of the procurement on a form provided by

ADB. The description and amount of the contract,

together with the name and address of the successful

bidder, shall be subject to release by ADB upon receipt

of the signed copy of the contract.

3. Modifications. In the case of contracts subject to prior review,

before granting a material extension of the stipulated time for

performance of a contract, agreeing to any modification or waiver

of the conditions of such contract, including issuing any change

order or orders under such contract (except in cases of extreme

urgency) which would in aggregate increase the original amount

of the contract by more than 15 percent of the original price, the

borrower shall seek ADB’s no objection to the proposed extension,

modification, or change order. If ADB determines that the proposal

would be inconsistent with the provisions of the financing

agreement and/or procurement plan, it shall promptly inform the

borrower and state the reasons for its determination. A copy of all

amendments to the contract shall be furnished to ADB for its record.

4. Translations. Contracts awarded under ICB must be written

in English. Any supporting documentation that might have

originated in another language (such as technical descriptions of

equipment) must be accompanied with an English translation.

Post Review

5. If ADB and the borrower have agreed on post review, ADB

will review and respond as soon as practicable, but no later than 6

months after receipt of the required documents, or it will be

assumed that ADB has no objection to the borrower’s action. The

borrower shall retain all documentation with respect to each

contract where post review is required during project

implementation and up to two years after the project closing date.

This documentation would include, but not be limited to, the signed

54 Procurement Guidelines

original of the contract, the evaluation report including the analysis

of the respective proposals, and recommendations for award, for

examination by ADB or by its consultants. Master copies of electronic

documents must be retained in print form, suitably authenticated

by the issuing agency by signature, stamp or other feature

acceptable to ADB. The borrower shall furnish such documentation

to ADB upon award of contract unless otherwise specified in the

financing agreement. If ADB determines that the goods, or works

were not procured in accordance with the agreed procedures as

reflected in the financing agreement, it may declare misprocurement

as established in paragraph 1.12 of the Guidelines. ADB shall

promptly inform the borrower the reasons for such determination.

If misprocurement is declared after disbursement, the borrower

shall refund the corresponding amount to ADB.

APPENDIX 1 ADB REVIEW OF PROCUREMENT DECISIONS 55

Appendix 2

DOMESTIC PREFERENCES

Preference for Domestically Manufactured Goods

1. The borrower may, with the agreement of ADB, grant a

margin of preference in the evaluation of bids under international

competitive bidding (ICB) procedures to bids offering

certain goods manufactured in the country of the borrower, when

compared to bids offering such goods manufactured elsewhere.

In such cases, bidding documents shall clearly indicate any

preference to be granted to domestic manufactured goods and

the information required to establish the eligibility of a bid for

such preference. The nationality of the manufacturer or supplier is

not a condition for such eligibility. The methods and stages set

forth hereunder shall be followed in the evaluation and comparison

of bids.

2. For comparison, responsive bids shall be classified in one of

the following three groups:

(a) Group A: bids exclusively offering goods manufactured

in the country of the borrower if the bidder establishes to

the satisfaction of the borrower and ADB that (i) labor,

raw material, and component from within the country of

the borrower will account for 30 percent or more of the

EXW price of the product offered, and (ii) the production

facility in which those goods will be manufactured or

assembled has been engaged in manufacturing/assembling

such goods at least since the time of bid submission.

(b) Group B: all other bids offering goods manufactured

in the country of the borrower.

56 Procurement Guidelines

(c) Group C: bids offering goods manufactured abroad that

have been already imported or that will be directly imported.

3. The price quoted for goods in bids of groups A and B shall

include all duties and taxes paid or payable on the basic materials

or component purchased in the domestic market or imported, but

shall exclude the sales and similar taxes on the finished product.

The price quoted for goods in bids of group C shall be on CIF or

CIP (place of destination), which is exclusive of customs duties

and other import taxes already paid or to be paid.

4. In the first step, all evaluated bids in each group shall be

compared to determine the lowest bid in each group. Such lowest

evaluated bids shall be compared with each other and if, as a result

of this comparison, a bid from group A or group B is the lowest,

it shall be selected for the award.

5. If as a result of the comparison under paragraph four above,

the lowest evaluated bid is a bid from group C, the lowest evaluated

bid from group C shall be further compared with the lowest

evaluated bid from group A after adding to the evaluated price of

goods offered in the bid from group C, for the purpose of this

further comparison only, an amount equal to 15 percent of the

CIF or CIP bid price. The lowest evaluated bid determined from this

last comparison shall be selected.

6. In the case of single responsibility, supply and installation or

turnkey48 contracts in which a number of discrete items of equipment

is grouped into one contract package or in a bid package

involving multiple items, the preference margin shall not be applied

to the whole package, but only to the locally manufactured equipment

within the package. Equipment offered from abroad shall be

APPENDIX 2 DOMESTIC PREFERENCES 57

48 These provisions apply only if customs duties are excluded from the bid prices, and the

price of imported goods quoted is on a CIF or CIP basis.

quoted CIF or CIP, and equipment offered locally EXW (free of sales

and similar taxes); and all other components, such as design, works,

installation, and supervision, shall be quoted separately. Bids should

not be classified into groups A, B, or C. In the comparison of bids,

only the CIF or CIP price in each bid of the equipment offered from

outside the borrower’s country shall be increased by 15 percent.

No preference shall be applied for any associated services or works

included in the package.

Preference for Domestic Contractors

7. For contracts for works to be awarded on the basis of ICB,

eligible borrowers may, with the agreement of ADB, grant a margin

of preference of 7.5 percent to domestic contractors,49 in accordance

with, and subject to, the following provisions:

(a) Contractors applying for such preference shall be asked

to provide, as part of the data for qualification,50 such

information, including details of ownership, as shall be

required to determine whether, according to the classification

established by the borrower and accepted by

ADB, a particular contractor or group of contractors

qualifies for a domestic preference. The bidding documents

shall clearly indicate the preference and the

method that will be followed in the evaluation and

comparison of bids to give effect to such preference.

(b) After bids have been received and reviewed by the

borrower, responsive bids shall be classified into the

following groups:

(i) Group A: bids offered by domestic contractors

eligible for the preference.

58 Procurement Guidelines

49 Preference for domestic Contractors is applicable only in countries which qualify.

50 At the prequalification and/or at the bidding stage.

(ii) Group B: bids offered by other contractors.

8. For the purpose of evaluation and comparison of bids, an

amount equal to 7.5 percent of the bid amount shall be added to

bids received from contractors in group B.

APPENDIX 2 DOMESTIC PREFERENCES 59

Appendix 3

GUIDANCE TO BIDDERS

Purpose

1. This appendix provides guidance to potential bidders wishing

to participate in ADB-financed procurement.

Responsibility for Procurement

2. The responsibility for the implementation of the project, and

therefore for the payment of goods, works, and services under the

project, rests solely with the borrower. ADB, for its part, is required

by its Charter to ensure that funds are paid from ADB financing

only as expenditures are incurred. Disbursements are made only at

the borrower’s request. Supporting evidence that the funds are

used in accordance with the financing agreement and/or the

procurement plan shall be submitted with the borrower’s

withdrawal application. Payment may be made (a) to reimburse

the borrower for payment(s) already made from its own resources,

(b) directly to a third party (usually to a supplier or contractor), or

(c) to a commercial bank for expenditures against a Commitment

Letter covering a commercial bank’s letter of credit.51 As emphasized

in paragraph 1.2 of the Guidelines, the borrower is legally

responsible for the procurement. It invites, receives, and evaluates

bids, and awards the contract. The contract is between the borrower

and the supplier or contractor. ADB is not a party to the contract.

ADB’s Role

3. As stated in paragraph 1.11 of the Guidelines, ADB reviews

the procurement procedures, documents, bid evaluations, award

recommendations, and the contract to ensure that the process is

51 A complete description of ADB’s disbursement procedures is provided in the Loan Disbursement

Handbook (available on ADB’s website at http://www.adb.org).

60 Procurement Guidelines

carried out in accordance with agreed procedures, as required in

the financing agreement. In the case of major contracts, the

documents are reviewed by ADB prior to their issue, as described

in Appendix 1. Also, if, at any time in the procurement process

(even after the award of contract), ADB concludes that the agreed

procedures were not followed in any material respect, ADB may

declare misprocurement, as described in paragraph 1.12. However,

if a borrower has awarded a contract after obtaining ADB’s “no

objection,” ADB will declare misprocurement only if the “no

objection” was issued on the basis of incomplete, inaccurate, or

misleading information furnished by the borrower. Furthermore, if

ADB determines that corrupt or fraudulent practices were engaged

in by representatives of the borrower or of the bidder, ADB may

impose the applicable sanctions set forth in paragraph 1.14 of the

Guidelines.

4. ADB has published Standard Bidding Documents (SBDs) for

various types of procurement. As stated in paragraph 2.12 of the

Guidelines, it is mandatory for the borrower to use these documents,

with minimum changes to address country- and projectspecific

issues. The prequalification and bidding documents are

finalized and issued by the borrower.

Information on Bidding

5. Information on bidding opportunities under ICB may be

obtained from the general procurement notice and the specific

procurement notices as described in paragraphs 2.7 and 2.8 of

the Guidelines. General guidance on participation, as well as advance

information on business opportunities in upcoming projects,

may be obtained from the ADB website.52

APPENDIX 3 GUIDANCE TO BIDDERS 61

52 http://www.adb.org.

Bidder’s Role

6. Once a bidder receives the prequalification or bidding

document, the bidder should study the documents carefully to

decide if it can meet the technical, commercial, and contractual

conditions, and if so, proceed to prepare its bid. The bidder should

then critically review the documents to see if there is any ambiguity,

omission, or internal contradiction, or any feature of specifications

or other conditions which are unclear or appear discriminatory or

restrictive; if so, it should seek clarification from the borrower, in

writing, within the time period specified in the bidding documents

for seeking clarifications.

7. The criteria and methodology for selection of the successful

bidder are outlined in the bidding documents, generally under

Instructions to Bidders and Specifications. If these are not clear,

clarification should be similarly sought from the borrower.

8. In this connection it should be emphasized that the specific

bidding documents issued by the borrower govern each procurement,

as stated in paragraph 1.1 of the Guidelines. If a bidder

feels that any of the provisions in the documents are inconsistent

with the Guidelines, it should also raise this with the borrower.

9. It is the responsibility of the bidder to raise any issue of

ambiguity, contradiction, omission, etc., prior to the submission

of its bid, to assure submission of a fully responsive and compliant

bid, including all the supporting documents requested in the

bidding documents. Noncompliance with critical (technical and

commercial) requirements will result in rejection of the bid. If a

bidder wishes to propose deviations to a noncritical requirement,

or propose an alternative solution, the bidder should quote the

price for the fully compliant bid and then separately indicate the

adjustment in price that can be offered if the deviation is accepted.

Alternative solutions should be offered only when authorized in

the bidding documents. Once bids are received and publicly opened,

62 Procurement Guidelines

bidders will not be required or permitted to change the price or

substance of a bid.

Confidentiality

10. As stated in paragraph 2.47 of the Guidelines, the process

of bid evaluation shall be confidential until the publication of

contract award. This is essential to enable the borrower and ADB

reviewers to avoid either the reality or perception of improper

interference. If at this stage a bidder wishes to bring additional

information to the notice of the borrower, ADB, or both, it should

do so in writing.

Action by ADB

11. Bidders are free to send copies of their communications on

issues and questions with the borrower to ADB or to write to ADB

directly, when borrowers do not respond promptly, or the

communication is a complaint against the borrower. All such

communications should be addressed to the project officer for the

project, with a copy to the Principal Director, Central Operations

Services Office.

12. References received by ADB from potential bidders, prior to

the closing date for submission of the bids, will, if appropriate, be

referred to the borrower with ADB’s comments and advice, for

action or response.

13. Communication received from bidders after the opening of

the bids, will be handled as follows. In the case of contracts not

subject to prior review by ADB, the communication will be sent to

the borrower for due consideration and appropriate action, if any,

and these will be reviewed during subsequent supervision of the

project by ADB staff. In the cases of contracts subject to the prior

review process, the communication will be examined by ADB, in

consultation with the borrower. If additional data is required to

APPENDIX 3 GUIDANCE TO BIDDERS 63

64 Procurement Guidelines

complete this process, these will be obtained from the borrower. If

additional information or clarification is required from the bidder,

ADB will ask the borrower to obtain it and comment or incorporate

it, as appropriate, in the evaluation report. ADB’s review will

not be completed until the communication is fully examined and

considered.

14. (a) Except for acknowledgment, ADB will not normally enter

into discussion or correspondence with any bidder

during the evaluation and review process of the

procurement, until award of the contract is published.

(b) Notwithstanding paragraph 14(a) above, ADB may enter

into discussion where it deems necessary to conduct

investigations, audit, evaluation or other assessments

of the procurement process.

Debriefing

15. As stated in paragraph 2.65, if, after notification of award,

a bidder wishes to ascertain the grounds on which its bid was not

selected, it should address its request to the borrower. If the bidder

is not satisfied with the explanation given and wishes to seek a

meeting with ADB, it may do so by writing the Principal Director,

Central Operations Services Office, who will arrange a meeting at

the appropriate level and with the relevant staff. In this discussion,

only the bidder’s bid can be discussed and not the bids of

competitors.

Asian Development Bank

6 ADB Avenue

.